## Exhibit A-SOW
Exhibit A - Project Scope of Work
Brief project description: ENTER BRIEF PROJECT SUMMARY FROM GRANT APPLICATION FORM
Task # | Task Name | Task Description | Quantifiable Results/Deliverables
1 | Invasive Removal and Habitat Restoration | This task will include a 3-year effort to mobilize and train volunteers to remove invasive plants threatening salt marsh bird’s-beak and Nuttall’s acmispon. Volunteers will be organized at least monthly in large community events during the winter-spring, and smaller events on an ongoing basis. In addition, volunteers will plant native plants in the adjacent upland to encourage pollinators to benefit rare species. These events will serve as a service learning opportunity, and will include a tour and education from project partners. | • Reduce invasive plant coverage to less than 20% coverage, tracked through mapping • Planting lists • Photomonitoring report
2 | Access Control | This task is designed to improve the physical barriers between the biological resources in the project area and recreational trails. This includes several components: first, evaluation of the performance of 2,800 feet of recently installed sand fences to inform the design of additional fencing needed to complete the protections of this area, upgrading remaining poor condition fencing (appx. 1,000 feet), and then training volunteers to maintain over 3,800 feet of access control barriers. | • Map of new fencing • Photo documentation of installed fence • Access control fence maintenance record
3 | Community Engagement, Education and Outreach | This task includes development and implementation of an engagement strategy to inspire behavioral change, increase public buy-in, leverage support of stakeholder groups, and engage the community in this highly visible restoration site. Engagement will include approximately monthly combination of presentations to community, on-site docent-led tours, virtual education and media, and attending community events throughout the project period. These events will allow us to reach 10,000+ people, especially neighbors. This task will also include at least 3 annual education experiences for students from nearby disadvantaged schools, hosted collaboratively by partners. In addition, large permanent interpretive panels will be designed and installed, plus smaller interpretive signs within the site. | • Log of volunteers numbers and hours • Log of students engaged and schools served • Report on community engagements • Photos and digital proof of interpretive materials
4 | Monitoring | This task includes working with City biologists to complete annual monitoring of rare plants and birds. We will also coordinate to collect and share data with other agencies. These protocols will be used to strengthen community science monitoring methods to further document reliable data of bird use of the project area, and changes in rare plant occurrence. | • IMG Monitoring Reports from City staff, annually • Community Monitoring Reports, annually
5 | Admin | This task will include budgeting, expense tracking, creation of invoices and progress reports, permitting, and administrative coordination with project partners and SANDAG. | • Invoices • Progress Reports • Deliverables update

## Exhibit B-Budget
Exhibit B - Project Budget
Grantee agrees to submit invoices to SANDAG on a quarterly basis within three weeks after period covering January 1 to March 31; within three weeks after period covering April 1 to June 30; within three weeks after period covering July 1 to September 30; and within three weeks after period covering October 1 to December 31; covering the costs of the work done by Task during that time period. Invoices should include backup material on the matching funds and the requested TransNet funds.
Task # | Task Name | Year 1 Grant Amount | Year 1 Matching Funds1 | Year 2 Grant Amount | Year 2 Matching Funds1 | Year 3 Grant Amount | Year 3 Matching Funds1 | Total Grant Amount | Total Matching Funds1 | Total Project Cost
1 | Invasive Removal and Habitat Restoration | 22448.54 | 67132.3 | 22213.46 | 67137.29 | 22865.01 | 67142.43 | 67527.01 | 201412.02 | 268939.03
2 | Access Control | 5691.67 | 8226.56 | 10045.04 | 15326.16 | 4579.88 | 3226.56 | 20316.59 | 26779.28 | 47095.87
3 | Community Engagement, Education and Outreach | 32338.86 | 10165.1 | 35150.63 | 10971.74 | 26633.24 | 10165.1 | 94122.73 | 31301.94 | 125424.67
4 | Monitoring | 10088.56 | 6272.2 | 9755.74 | 6272.2 | 10031.01 | 6272.2 | 29875.31 | 18816.6 | 48691.91
5 | Administration | 8530.24 | 975.75 | 8933.86 | 1005.02 | 9356.97 | 1035.17 | 26821.07 | 3015.94 | 29837.01
Subtotal |  | 79097.87 | 92771.91 | 86098.73 | 100712.41 | 73466.11 | 87841.46 | 238662.71 | 281325.78 | 519988.49
TOTAL |  | 79097.87 | 92771.91 | 86098.73 | 100712.41 | 73466.11 | 87841.46 | 238662.71 | 281325.78 | 519988.49
PERCENTAGE |  | 15.21% | 17.84% | 16.56% | 19.37% | 14.13% | 16.89% | 45.9% | 54.1% | 100%
Task # | Task Name | Year 1 Grant Amount | Year 1 Matching Funds1 | Year 2 Grant Amount | Year 2 Matching Funds1 | Year 3 Grant Amount | Year 3 Matching Funds1 | Total Grant Amount | Total Matching Funds1 | Total Project Cost
1 | Invasive Removal and Habitat Restoration | 22448.54 | 63574.75 | 22213.46 | 63579.74 | 22865.01 | 63584.88 | 67527.01 | 190739.37 | 258266.38
2 | Access Control | 5691.67 | 8226.56 | 10045.04 | 15326.16 | 4579.88 | 3226.56 | 20316.59 | 26779.28 | 47095.87
3 | Community Engagement, Education and Outreach | 30234.98 | 9560.12 | 32579.88 | 10366.76 | 24592.27 | 9560.12 | 87407.13 | 29487 | 116894.13
4 | Monitoring | 10088.56 | 6272.2 | 9755.74 | 6272.2 | 10031.01 | 6272.2 | 29875.31 | 18816.6 | 48691.91
5 | Administration | 8530.24 | 975.75 | 8933.86 | 1005.02 | 9356.97 | 1035.17 | 26821.07 | 3015.94 | 29837.01
Subtotal |  | 76993.99 | 88609.38 | 83527.98 | 96549.88 | 71425.14 | 83678.93 | 231947.11 | 268838.19 | 500785.3
TOTAL |  | 76993.99 | 88609.38 | 83527.98 | 96549.88 | 71425.14 | 83678.93 | 231947.11 | 268838.19 | 500785.3
PERCENTAGE |  | 15.37% | 17.69% | 16.68% | 19.28% | 14.26% | 16.71% | 46.32% | 53.68% | 100%
1 Throughout the Project, Matching Funds must be proportionate to TOTAL Project Costs (Grant Amount and Matching Funds combined)

## Exhibit C-Schedule
Exhibit C - Project Schedule
Task # | Task Name | Task Start Date1 | Months Needed to Complete Task | Task End Date
1 | Invasive Removal and Habitat Restoration | 36 Months from NTP | 36 Months | 10/31/25
2 | Access Control | 36 Months from NTP | 36 Months | 10/31/25
3 | Community Engagement, Education and Outreach | 36 Months from NTP | 36 Months | 10/31/25
4 | Monitoring | 36 Months from NTP | 36 Months | 10/31/25
5 | Administration | 36 Months from NTP | 36 Months | 10/31/25
1 Assumes Fall 2022 Notice to Proceed. PLEASE INSERT ADDITIONAL NOTES ON WHY AND HOW MUCH ADDITIONAL TIME WOULD BE NEEDED 1) IN THE EVENT OF A SIGNIFICANTLY DELAYED NTP BEYOND Fall 2022; AND 2) UNEXPECTED WEATHER CONDITIONS SUCH AS DROUGHT THAT COULD OCCUR DURING THE PROPOSED PROJECT IMPLEMENTATION
Based on the proposed timeline of this project, if the Notice To Proceed was delayed beyond Fall 2022 or if weather becomes an insurmountable issue, the project would need to be extended by 3- 6 months depending on the length of delay or weather hold. This would allow for the project to complete the last growing season and allow for full weed control activities to be completed during the prime growing season. With a multi-year effort, initial start-up delays will be less impactful over the life of the project, and we can adjust the schedule accordingly without disrupting the goals and objectives of the project. Weather, is a larger factor, particularly extremely low or extremely heavy precipitation in a given year. Extreme weather trends that last over multiple growing seasons may result in a shift of focus either expanding or contracting the restoration areas in response the extreme weather to ensure the long-term viability of the restored habitats/species.