San Diego Association of Governments

Ocean Beach Estuary Enhancement Project

The San Diego River Park Foundation (SDRPF)

Quarterly Progress Report

Reporting Period:  01/01/24 – 03/31/24

Submission Date:  04/22/24

SANDAG Contract Number:  S1125510

Quarterly Status Report Overview

PLEASE DO NOT CHANGE OR ALTER THE FORMATTING OF THIS DOCUMENT! SANDAG has developed a standardized grant monitoring and tracking program for the Environmental Mitigation Program (EMP) Land Management Grant Program. The purpose is to collect information on individual projects and the grant program as a whole for reporting to the Regional Habitat Conservation Taskforce, SANDAG Policy Advisory Committees, and the SANDAG Board of Directors. SANDAG monitors grantees through invoices, progress reports, performance measures, and designated photograph points. These standardized reporting templates and instructions for submittal are included below.

# Work Performed this Period:

## Task 1 - Invasive Removal and Habitat Restoration

Because most of the invasive removal portion of our restoration project requires a Coastal Development Permit that has not yet been awarded, we continue to focus on planning and securing the permit (see Task 5 discussion of permit status).  The SDRPF staff continues to conduct internal meetings and collaborate with project partners to expedite permit proceedings, strategize for the pre-permit phase, and ensure preparedness for the prompt commencement of work once the permits are approved.

SDRPF staff also, in conjunction with City staff, planned for volunteer work parties to engage the community in invasive removal.  While the exact timeline of permit award is still pending, there is significant growth of invasive non-native plants like crown daisy (Glebionis coronaria), sea rocket (Cakile maritima) and curly dock (Rumex crispus) occurring in existing pathways, which can be targeted for removal now.

In cooperation with the City Ranger, the first of these events was scheduled for 3/31, but had to be rescheduled to Q2 due to rain.  While these first events will focus on weeding existing pathways, they will help build momentum with community volunteers who can pivot to the habitat area once the permits are awarded, while still benefiting the habitat area by reducing the population of invasive plants.

10% complete.

## Task 2 - Access Control

No field work has been completed for this task while project partners await permits to begin installing the access control fencing.

Staff continued to meet with the City of San Diego (the lead applicant for the permits) about the permit process.  See Task 5 for discussion of permit status.

2.9% complete.

## Task 3 - Community Engagement, Education and Outreach

Community engagement staff continued planning for outreach events and met with representatives of organizations in the Ocean Beach/Point Loma community to work on establishing a visible, long-term presence at the River Mouth.  Staff posted flyers in local businesses and public posting boards and met with organizations such as San Diego Audubon Society, Friends of Point Loma Native Plant Garden, and Coastal Sage Gardening.

SDRPF education staff have had several meetings with San Diego Audubon Society partners to create events for youth and the local community to mentor an understanding of the importance of sharing this vital area across multiple species and protecting the estuary habitat.  The first of these events will be on May 19, where participants will be able to grasp the impact canines have on the biodiversity and sensitivity ecosystem of a wide array of vulnerable birds.

Community engagement staff continued planning for outreach events.  Staff posted flyers in local businesses and public posting boards and met with organizations such as the Friends of Point Loma Native Plant Garden, and Coastal Sage Gardening to present to their volunteers or plan future collaboration.

Outreach partners from the San Diego Audubon Society held one railwatching and docent program per week at the River Mouth between January and March, engaging 12 volunteers.

23% complete.

## Task 4 – Monitoring

This quarter, SDRPF implemented a community science bioblitz to document the flora and fauna present across different habitat types in the project area. The event was initially scheduled for February 2 to align with World Wetlands Day, but postponed due to weather to February 9, engaging 6 volunteers. Volunteers and staff observed 49 different species with nearly 100 individual observations, recorded and saved via iNaturalist.

Additionally, SDRPF staff participated in the 2024 Rare Plant Inspect and Manage Training, conducted by the San Diego Management and Monitoring Program (SDMMP). This training will help staff to participate in rare plant monitoring scheduled for Q2 on the project site’s two rare plants: Nuttall's acmispon (Acmispon prostratus) and salt marsh bird's beak (Chloropyron maritimum). Furthermore, SDRPF will conduct an assessment for coastal woolly heads (Nemacaulis denudata), which is considered a 1B.2 species in California. These surveys are all anticipated to occur during bloom periods in Q2.

Our partners at San Diego Audubon Society completed two Ridgway’s rail surveys during this period in the area starting at the project site and continuing immediately upstream from the project area:  a King Tide survey of the River Mouth on February 9 (rescheduled from January 11 due to weather), and a survey with the regional coordinator of Ridgway’s Rail monitoring, Dick Zembal, on March 26.  4 Ridgway’s rails were observed in the February 9 survey.  On March 26, they recorded 13 pairs and 5 males in the San Diego River Estuary upstream of the project area.  These surveys engaged 29 volunteers.

28.8% complete

## Task 5 - Administration

Project administration this quarter included submitting our third invoice and progress report, and working with SANDAG and the San Diego Audubon Society to ensure compliance with various project requirements.  Staff coordinated with the City of San Diego to document and report on their in-kind matching funds.  Project admin also included other correspondence with partners and SANDAG, updating budgets and coordinating timesheets and reports both internally and from partner organizations.

In addition, staff continued to meet with the City of San Diego and SDAS at least monthly about the permits to enable this project.  As previously reported, the invasive removal, fencing and some signage will require a Coastal Development Permit from the California Coastal Commission.  The City of San Diego (as the landowner) is the lead for this application, and SDAS and SDRPF named partners in completing the work.

The Coastal Commission has indicated that once local permits were in place, the project could be considered.  During this quarter, we finally received approval of the Site Development Permit from the City of San Diego Development Services, and are ready to move to the next step with getting on the Coastal Commission’s agenda.  All project partners discussed the remaining questions from the Coastal Commission, so that the City has everything needed to get on the agenda.

20.3% complete.

Provide the exact work start date, a description of the work completed under each task, and percent complete. Add additional tasks as necessary

# Work Anticipated Next Period

This does not need to be task specific but should include a short paragraph or bullet point list of activities anticipated for next quarter.

Now that the Site Development Permit has been approved, the permit will be recorded with the County and the State Clearinghouse.  The City of San Diego will also now provide this permit to the Coastal Commission so that we may get the project on their calendar for approving the Coastal Development Permit.

While winter weather delayed some of the planned invasive removal work parties in the first quarter of 2024, those have been rescheduled for Q2.  Until the permit is awarded, this work will be limited to the City of San Diego’s current maintenance area around existing trails in the project area, but will be expanded into the habitat area as soon as allowable.

Community outreach and volunteer will continue with the monitoring and educational events planned, such as a bioblitz community monitoring event on April 26 and educational outreach event scheduled for May 19.  Staff will work with City of San Diego Natural Resources staff to complete rare plant monitoring during the appropriate windows in spring 2024, and San Diego Audubon Society staff and volunteers will continue bird monitoring as well as launch the Bark Ranger program in June.

# Issues to Note

Please provide a brief description of any issue(s) encountered during the reporting period and any steps taken to address the issue(s).

As discussed in the Task 5 report above, the permitting for the project is taking longer than anticipated.  We are working with the City of San Diego (the permit applicant) to resolve the remaining questions to submit the final permit package for review and award.

# Photographs & Figures

Photographs and figures are invaluable! Please include photos in the Quarterly Progress Reports and any figures (if applicable). Both photos and figures may be included throughout the document under corresponding tasks or at the end following the Issues to Note section.  Photographs taken at the same place or photographic points (photo-points) can assist SANDAG staff in tracking the project’s progress over time.

It is required that Photographs include:

- A before and after comparison sequence from the start to the completion of the project for photo points.

- A brief description of the corresponding tasks, date, and activity in the photograph.

- A copy of each photograph included in the report submitted in a .jpeg or .png file format.

It is required that Figures include:

- A caption with a brief description.

No photos provided this period.

SDMMP Project Page

To receive reimbursement for work conducted within the quarter, submission of Quarterly Progress, Annual, and Final Reports must be added to your project’s Project Page on the SDMMP website. Add any necessary photographs to the photo carousal and fill out the photograph information. Please contact Sarah McCutcheon (smccutcheon@usgs.gov) or Emily Perkins (eperkins@usgs.gov) if you are having trouble accessing or editing your project page.

Project Performance Measures Instructions

SANDAG will utilize the SANDAG Performance Measures to document compliance with the Project. Grantee’s performance will be measured against the Performance Measures (Exhibit D) during the term of the project. More details on Performance Measures and Grant Recovery Plans are outlined in the Grant Agreements.

To access the Project Performance Measures Excel Spreadsheet:

- Simply double-click on the Excel icon located under the Project Performance Measures section.

  - An excel sheet will open, please fill out and then click save.

- Once the Excel spreadsheet is saved, please exit Excel and the spreadsheet will automatically update the icon in the Quarterly Progress Report Word document.

When opening the document with the Project Performance Measures Excel Spreadsheet:

- When you first open the Quarterly Progress Report Template, a warning message will open (image of the warning message below)

  - Click Yes to update the links in the document.

# Performance Measures

Please include the Project’s Performance Measures for each Quarterly Invoice and Progress Report in order to receive reimbursement.