San Diego Association of Governments

Ocean Beach Estuary Enhancement Project

The San Diego River Park Foundation (SDRPF)

Quarterly Progress Report

Reporting Period:  10/01/25 – 12/31/25

Submission Date:  01/22/26

SANDAG Contract Number:  S1125510

Quarterly Status Report Overview

PLEASE DO NOT CHANGE OR ALTER THE FORMATTING OF THIS DOCUMENT! SANDAG has developed a standardized grant monitoring and tracking program for the Environmental Mitigation Program (EMP) Land Management Grant Program. The purpose is to collect information on individual projects and the grant program as a whole for reporting to the Regional Habitat Conservation Taskforce, SANDAG Policy Advisory Committees, and the SANDAG Board of Directors. SANDAG monitors grantees through invoices, progress reports, performance measures, and designated photograph points. These standardized reporting templates and instructions for submittal are included below.

# Work Performed this Period:

## Task 1 - Invasive Removal and Habitat Restoration

This quarter, staff advanced habitat restoration by increasing efforts to complete invasive plant removal across the project area. Together with volunteers, they targeted annual weeds, concentrating work in plots where sensitive native species, like Nuttall’s acmispon, salt marsh bird’s beak, and coast wooly heads are most abundant. These efforts aim to reduce competition from invasive plants and promote the rare native plants (see Photos 1- 4).

Photos 1-4: Volunteers hand-pulling in the project area to remove annual weeds.

Primary non-native annual weeds targeted for removal included crown daisy (Glebionis coronaria), devil’s thorn (Rumex spinosus), European sea rocket (Cakile maritima), prickly Russian thistle (Salsola tragus), and European sea lavender (Limonium duriusculum).

The San Diego River Park Foundation (SDRPF) hosted 11 restoration events this quarter, engaging 135 community volunteers who contributed a combined 373 service hours. In addition, project partners from the San Diego Bird Alliance (SDBA) began hosting First Friday restoration events, which started with a restoration project held as part of San Diego Climate Week, and continued monthly. During these events, SDBA staff guided volunteers in 33 hours of service to remove invasive annual weeds, repair and extend access control, and remove trash from the project area.

Not only was significant progress made in terms of reaching restoration goals, but these events served as educational opportunities for kids and adults alike. We raised awareness about the significant ecological value of native species and the negative impacts invasive plants pose on the surrounding ecosystem. (see Photos 5-8). The removal work completed this quarter is especially timely as we head into the rainy season where we are starting to see rare native seedlings looking for space and nutrients to establish. These efforts are essential to promoting a more resilient, biodiverse, and functional ecosystem.

Photos 5-8: Group photos of volunteers before and during Q4 restoration events

66% complete

## Task 2 - Access Control

In Quarter 4, access control fencing installation was completed with the final 198.7 linear feet installed. Additionally, damaged wooden slats along the existing fence were repaired or replaced on a regular basis to prevent further vandalism. This project more securely reinforces boundaries and helps protect the sensitive habitat areas of the estuary (see photos 9-12).  An updated map of completed fencing is included here as Figure 1 (see following page).

Photos 9-12: New fencing was installed and the existing fence was repaired by volunteers

Figure 1.  Map of completed access control fencing.

94% complete

## Task 3 - Community Engagement, Education and Outreach

Project partners from the SDBA held 3 monthly docent shifts in Q4, during which they conducted public outreach and education in the project area.

SDRPF held additional education and outreach activities, both in conjunction with volunteer events and docent activities with SDBA and at dedicated tabling events over the busy days at the beach during the winter holidays.  During these events, staff spoke to visitors to Dog Beach and the River Mouth, trail users along the San Diego River Trail and neighbors to the project area. During these activities, staff raised awareness about the project, about the ecological importance of the area, and worked to recruit for upcoming volunteer activities.

42% complete.

## Task 4 – Monitoring

In Q4, SDRPF staff coordinated Research & Restoration interns to complete photomonitoring of the general habitat conditions of the San Diego River Estuary in 16 different locations (see Figure 2).  This allows us to monitor change over time as restoration progresses (see Photo 13 on following page).

In addition, SDBA staff organized 6 railwatching programs in Q4.  (Tern nesting season is over, so monitoring focused on Ridgway’s rails.) Staff also coordinated with the City of San Diego to access the estuary via kayak to during King Tides to survey for sensitive bird species.  Accessing the area during the unusually high tide gives better access to the estuary without disturbing the sensitive mudflats.  Surveyers did not observe any rails, but they documented one Belding’s savannah sparrow (Passerculus sandwichensis, an endangered species), and unfortunately also observed floating trash.

76% complete.

Figure 2.  Photomonitoring locations in and around the project area

Photo 13:  sample of photos over time from Photo Monitoring Location #2.

## Task 5 - Administration

Project administration this quarter included submitting our tenth invoice and progress report, and working with SANDAG and the San Diego Bird Alliance to ensure compliance with various project requirements. Staff coordinated with the City of San Diego to document and report on their in-kind matching funds.  Staff also reached out to SANDAG staff to extend the project end date to June 30, 2026.  This resulted from discovering an inconsistency in the grant agreement that indicated two different end dates.  In consultation with project partners, we decided to request an extension to the end of the quarter to ensure sufficient time for reporting.

Project admin also included other correspondence with partners and SANDAG, updating budgets and coordinating timesheets and reports both internally and from partner organizations.  In addition, staff continued to meet with the City of San Diego and San Diego Birding Alliance at least monthly about the permits, collaboration on events, and coordination on dealing with maintenance issues.

81% complete.

Provide the exact work start date, a description of the work completed under each task, and percent complete. Add additional tasks as necessary

# Work Anticipated Next Period

This does not need to be task specific but should include a short paragraph or bullet point list of activities anticipated for next quarter.

In Q1 of 2026, we anticipate significant germination of invasive weeds, and will organize regular events to target early removal before annuals go to seed. We will organize at least one planting event to continue to encourage native plant re-establishment in the restored areas.  We will continue public outreach efforts, including completing a final draft of the interpretive panel and other signage.  On the administrative side, we will submit the request to extend the project date to June 30, and discuss with our SANDAG point of contact options to ensure we meet the match requirements.

# Issues to Note

Please provide a brief description of any issue(s) encountered during the reporting period and any steps taken to address the issue(s).

As we approach the end of this grant period, we are reviewing the remaining funds and match.  We foresee the potential need to adjust match targets between tasks in order to meet overall project match, and will be reaching out to discuss this option and process with SANDAG staff.

# Photographs & Figures

Photographs and figures are invaluable! Please include photos in the Quarterly Progress Reports and any figures (if applicable). Both photos and figures may be included throughout the document under corresponding tasks or at the end following the Issues to Note section.  Photographs taken at the same place or photographic points (photo-points) can assist SANDAG staff in tracking the project’s progress over time.

It is required that Photographs include:

- A before and after comparison sequence from the start to the completion of the project for photo points.

- A brief description of the corresponding tasks, date, and activity in the photograph.

- A copy of each photograph included in the report submitted in a .jpeg or .png file format.

It is required that Figures include:

- A caption with a brief description.

Photos are in document above and also submitted as separate files.

SDMMP Project Page

To receive reimbursement for work conducted within the quarter, submission of Quarterly Progress, Annual, and Final Reports must be added to your project’s Project Page on the SDMMP website. Add any necessary photographs to the photo carousal and fill out the photograph information. Please contact Sarah McCutcheon (smccutcheon@usgs.gov) or Emily Perkins (eperkins@usgs.gov) if you are having trouble accessing or editing your project page.

Project Performance Measures Instructions

SANDAG will utilize the SANDAG Performance Measures to document compliance with the Project. Grantee’s performance will be measured against the Performance Measures (Exhibit D) during the term of the project. More details on Performance Measures and Grant Recovery Plans are outlined in the Grant Agreements.

To access the Project Performance Measures Excel Spreadsheet:

- Simply double-click on the Excel icon located under the Project Performance Measures section.

  - An excel sheet will open, please fill out and then click save.

- Once the Excel spreadsheet is saved, please exit Excel and the spreadsheet will automatically update the icon in the Quarterly Progress Report Word document.

When opening the document with the Project Performance Measures Excel Spreadsheet:

- When you first open the Quarterly Progress Report Template, a warning message will open (image of the warning message below)

  - Click Yes to update the links in the document.

Performance Measures

Please include the Project’s Performance Measures for each Quarterly Invoice and Progress Report in order to receive reimbursement.